## Team
Initials | First | Last | Email | GitHub Username
ls | Lauren | Sachs | lsachs@stevens.edu | lsachs98
ma | Mario | Alexandre | malexan3@stevens.edu | SecondThrow
tm | Taleen | Mitchell | tmitche2@stevens.edu | tmitche2
|  |  | GitHub Repository: | https://github.com/lsachs98/cs555

## Backlog
Sprint | Story ID | Story Name | Owner | Status
1 | US09 | Birth before death of parents | ma | done
1 | US11 | No bigamy | ma | done
1 | US01 | Dates before current date | tm | done
1 | US02 | Birth before marriage | tm | done
1 | US28 | Order siblings by age | ls | done
1 | US29 | List deceased | ls | done
2 | US05 | Marriage before death | tm | done
2 | US06 | Marriage before divorce | tm | done
2 | US12 | Parents not too old | ma | done
2 | US13 | Siblings spacing | ma | done
2 | US30 | List living married | ls | done
2 | US31 | List living single | ls | done
3 | US03 | Birth before death | tm | done
3 | US06 | Divorce before death | tm | done
3 | US17 | No marriages to descendants | ma | done
3 | US18 | Siblings should not marry | ma | done
3 | US35 | List recent births | ls | done
3 | US36 | List recent deaths | ls | done
4 | US07 | Less than 150 years old | tm | done
4 | US10 | Marriage after 14 | tm | done
4 | US15 | Fewer than 15 siblings | ma | done
4 | US16 | Male last names | ma | done
4 | US38 | Upcoming birthdays | ls | done
4 | US42 | Reject illegitemate birthdays | ls | done

## Burndown README
The goal of the burndown chart is to help the agile team and customer to understand how the developers are doing
to deliver the product. Burndown charts can be done daily, weekly, at the end of a sprint, or at whatever time interval makes sense.
We'll update our burndown chart for the GEDCOM project at the end of each sprint.
At the end of each sprint, you should update the number of remaining stories, the LOC written to implement the user stories
implemented in this sprint, and the minutes needed to write those lines of code.
Here's a sample burndown chart for a team of three:
Sprint | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Start | 2016-06-06 | 24 |  | 0
Sprint 1 | 2016-06-19 | 18 | 6 | 250 | 120 | 125
Sprint 2 | 2016-07-03 | 12 | 6 | 480 | 135 | 102.2222
Sprint 3 | 2016-07-17 | 6 | 6 | 740 | 160 | 97.5
Sprint 4 | 2016-07-31 | 0 | 6 | 1100 | 145 | 148.9655
= # team members * 4 sprints *
2 stories per sprint
lines of code per hour is calcuated by Excel
Velocity of completing user stories (calculated)
Total
LOC
How long to implement the user stories in this sprint
When we expect to complete all user stories

## Burndown
Start | Date | Remaining Stories | Story Velocity | LOC | Min | Code Velocity
Sprint 1 | 2019-02-20 | 18 | 6 | 300 | 350 | 51.4286
Sprint 2 | 2019-03-06 | 12 | 6 | 109 | 234 | 27.9487
Sprint 3 | 2019-04-10 | 6 | 6 | 108 | 264 | 24.5455
Sprint 4 | 2019-04-25 | 0 | 6 | 89 | 60 | 89

## Sprint1
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US09 | Birth before death of parents | ma | done | 200 | 120 | 70 | 60 | X
T09.01 | Store birth date | ma | [5 empty] | X
T09.02 | Find parents | ma | [5 empty] | X
T09.03 | Store death date of parents | ma | [5 empty] | X
T09.04 | Compare birth and death date of parents | ma | [5 empty] | X
US11 | No bigamy | ma | done | 200 | 120 | 100 | 75 | X
T11.01 | Find all marriage records for individual | ma | [5 empty] | X
T11.02 | Retirieve dates of all marriages | ma | [5 empty] | X
T11.03 | Compare dates of all marriages to check for overlap | ma | [5 empty] | X
US01 | Dates before current date | tm | done | 250 | 100 | 73 | 60 | x
T01.01 | Find current date | tm | [5 empty] | x
T01.02 | Retirieve dates of birth,death,divorce.marriage,etc. | tm | [5 empty] | x
T01.03 | Compare dates to current date and return any dates that are after | tm | [5 empty] | x
US02 | Birth before marriage | tm | done | 150 | 80 | 59 | 60 | x
T02.01 | Find birth date | tm | [5 empty] | x
T02.02 | Retirieve date(s) of marriage | tm | [5 empty] | x
T02.03 | Compare date(s) of marriage to date of birth and return false if before | tm | [5 empty] | x
US28 | Order siblings by age | ls | done | 250 | 120 | 100 | 120 | x
T28.01 | Retrieve siblings | ls | [5 empty] | x
T28.02 | Retrieve sibling ages | ls | [5 empty] | x
T28.03 | Order siblings by age | ls | [5 empty] | x
US29 | List deceased | ls | done | 200 | 100 | 10 | 30 | x
T29.01 | Find if the individual has a deceased date | ls | [5 empty] | x
T29.02 | Add to list | ls | [5 empty] | x
Review Results
| Keep doing: | Checking up on progress
Constant communication via. Groupme
| Work on: | Publishing user stories earlier so we can test
Less procrastination- finish the sprint days before the due date
Work with partners more (Pair programming) to solve some errors

## Sprint2
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US05 | Marriage before death | tm | done | 100 | 60 | 30 | 50 | x
T05.01 | Retrieve marriage date | tm | [5 empty] | x
T05.02 | Retrieve death date (if exists) | tm | [5 empty] | x
T05.03 | Compare values and return if any deaths before marriage | tm | [5 empty] | x
US04 | Marriage before divorce | tm | done | 100 | 60 | 25 | 30 | x
T04.01 | Retrieve marriage date | tm | [5 empty] | x
T04.02 | Retrieve divorce date(if exists) | tm | [5 empty] | x
T04.03 | Compare values and return if any divorces before marriage | tm | [5 empty] | x
US12 | Parents not too old | ma | done | 150 | 100 | 21 | 60 | x
T12.01 | Retrieve birthdates of parents | ma | [5 empty] | x
T12.02 | Retrieve birthdates of children | ma | [5 empty] | x
T12.03 | Calculate difference in age | ma | [5 empty] | x
T12.04 | If mother>60 or father>80, return false | ma | [5 empty] | x
US13 | Siblings spacing | ma | done | 100 | 80 | 13 | 44 | x
T13.01 | Retrieve birthdates of children | ma | [5 empty] | x
T13.02 | Calculate days between sibling age | ma | [5 empty] | x
T13.03 | If age<8months and age>2days, return false | ma | [5 empty] | x
x
US30 | List living married | ls | coding | 60 | 60 | 10 | 30 | x
T30.01 | Check if person is married | ls | [5 empty] | x
T30.02 | Check if person has death date, do not include in list if so | ls | [5 empty] | x
T30.03 | Return list | ls | [5 empty] | x
US31 | List living single | ls | coding | 90 | 80 | 10 | 20 | x
T31.01 | Go through each individual's name | ls | [5 empty] | x
T31.02 | Compare individual's name to any wife names or husband names | ls | [5 empty] | x
T31.03 | Return individual's name if they are not a wife or husband | ls | [5 empty] | x
Review Results
Keep doing: | Checking up on progress
Constant communication via. Groupme
Publishing user stories earlier so we can test
Work with partners more (Pair programming) to solve some errors
Work on: | Create test standards
Create test suite for easy regression testing
Refactor code together to make future sprints easier

## Sprint3
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US03 | Birth before death | tm | done | 50 | 45 | 15 | 30 | x
T03.01 | Check if death date exists | tm | [5 empty] | x
T03.02 | Check if death date is before birth date | tm | [5 empty] | x
T03.03 | Show individuals if death is before birth and return false, true otherwise | tm | [5 empty] | x
US06 | Divorce before death | tm | done | 70 | 60 | 21 | 40 | x
T06.01 | Check wife and husband in family | tm | [5 empty] | x
T06.02 | If divorce exists, match individual's name to the wife or husband | tm | [5 empty] | x
T06.03 | Check if death exists, compare to divorce date | tm | [5 empty] | x
T06.04 | Show individuals that have incorrect dates, return false, true otherwise | tm | [5 empty] | x
US17 | No marriages to descendants | ma | done | 150 | 100 | 22 | 104 | x
T17.01 | make list of descendants | ma | [5 empty] | x
T17.02 | check if any individual names are the same as wife/husband name | ma | [5 empty] | x
T17.03 | return false any names are the same | ma | [5 empty] | x
US18 | Siblings should not marry | ma | done | 80 | 75 | 12 | 30 | x
ma
T18.01 | Check childrens names under families | ma | [5 empty] | x
T18.02 | Check if children are a wife or husband | ma | [5 empty] | x
T18.03 | Make sure spouse's name is not the same | ma | [5 empty] | x
US35 | List recent births | ls | done | 60 | 45 | 19 | 30 | x
T35.01 | Check birth dates | ls | [5 empty] | x
T35.02 | If birth date is within past year (using datetime), add to list | ls | [5 empty] | x
US36 | List recent deaths | ls | done | 70 | 60 | 19 | 30 | x
T36.01 | Check death dates | ls | [5 empty] | x
T36.02 | If death date is within past year (using datetime), add to list | ls | [5 empty] | x
Keep doing: | Checking up on progress
Constant communication via. Groupme
Publishing user stories earlier so we can test
Work with partners more (Pair programming) to solve some errors
Work on: | Improve test standards
Refactor
Finish sprint doc earlier

## Sprint4
Story ID | Story Name | Owner | Status | Est Size | Est Time | Act Size | Act Time | Completed
US07 | Less than 150 years old | tm | done | 30 | 60 | 10 | 25 | x
T07.01 | check if individual is alive | tm | [5 empty] | x
T07.02 | take birthdate and add 150 years | tm | [5 empty] | x
T07.03 | if date in 150 years is before current date, return false | tm | [5 empty] | x
US10 | Marriage after 14 | tm | done | 40 | 75 | 29 | 30 | x
T10.01 | Check if individual has a wife or husband | tm | [5 empty] | x
T10.02 | Then check birth date and add 14 years | tm | [5 empty] | x
T10.03 | If individual turns 14 after before marriage date return false | tm | [5 empty] | x
US15 | Fewer than 15 siblings | ma | done | 20 | 45 | 10 | 10 | x
T15.01 | check if family has children | ma | [5 empty] | x
T15.02 | if children array length is greater than 15, return false | ma | [5 empty] | x
US16 | Male last names | ma | done | 50 | 60 | 13 | 50 | x
T16.01 | check if family has children | ma | [5 empty] | x
T16.02 | if they have children, get the last name of the father | ma | [5 empty] | x
T16.03 | for every male child, check their last name | ma | [5 empty] | x
T16.04 | if male child's last name does not match with father's last name, return false | ma | [5 empty] | x
US38 | Upcoming birthdays | ls | done | 15 | 30 | 15 | 30 | x
T38.01 | Retrieve their birth date | ls | [5 empty] | x
T38.02 | Construct a datetime object with their birth month | ls | [5 empty] | x
T38.03 | Compare the constructed datetime to 30 days from the runtime | ls | [5 empty] | x
US42 | Reject illegitemate birthdays | ls | done | 20 | 30 | 12 | 30 | x
T42.01 | Check if the birth and death dates are included | ls | [5 empty] | x
T42.02 | Check if included dates occur in a leap year and adjust max date in february accordingly | ls | [5 empty] | x
T42.03 | Check that the day is within the max number of days for the month | ls | [5 empty] | x
[6 empty] | 89 | 60

## Stories
Story ID | Story Name | Story Description
US01 | Dates before current date | Dates (birth, marriage, divorce, death) should not be after the current date
US02 | Birth before marriage | Birth should occur before marriage of an individual
US03 | Birth before death | Birth should occur before death of an individual
US04 | Marriage before divorce | Marriage should occur before divorce of spouses, and divorce can only occur after marriage
US05 | Marriage before death | Marriage should occur before death of either spouse
US06 | Divorce before death | Divorce can only occur before death of both spouses
US07 | Less then 150 years old | Death should be less than 150 years after birth for dead people, and current date should be less than 150 years after birth for all living people
US08 | Birth before marriage of parents | Children should be born after marriage of parents (and not more than 9 months after their divorce)
US09 | Birth before death of parents | Child should be born before death of mother and before 9 months after death of father
US10 | Marriage after 14 | Marriage should be at least 14 years after birth of both spouses (parents must be at least 14 years old)
US11 | No bigamy | Marriage should not occur during marriage to another spouse
US12 | Parents not too old | Mother should be less than 60 years older than her children and father should be less than 80 years older than his children
US13 | Siblings spacing | Birth dates of siblings should be more than 8 months apart or less than 2 days apart (twins may be born one day apart, e.g. 11:59 PM and 12:02 AM the following calendar day)
US14 | Multiple births <= 5 | No more than five siblings should be born at the same time
US15 | Fewer than 15 siblings | There should be fewer than 15 siblings in a family
US16 | Male last names | All male members of a family should have the same last name
US17 | No marriages to descendants | Parents should not marry any of their descendants
US18 | Siblings should not marry | Siblings should not marry one another
US19 | First cousins should not marry | First cousins should not marry one another
US20 | Aunts and uncles | Aunts and uncles should not marry their nieces or nephews
US21 | Correct gender for role | Husband in family should be male and wife in family should be female
US22 | Unique IDs | All individual IDs should be unique and all family IDs should be unique
US23 | Unique name and birth date | No more than one individual with the same name and birth date should appear in a GEDCOM file
US24 | Unique families by spouses | No more than one family with the same spouses by name and the same marriage date should appear in a GEDCOM file
US25 | Unique first names in families | No more than one child with the same name and birth date should appear in a family
US26 | Corresponding entries | All family roles (spouse, child) specified in an individual record should have corresponding entries in the corresponding family records. Likewise, all individual roles (spouse, child) specified in family records should have corresponding entries in the corresponding individual's records. I.e. the information in the individual and family records should be consistent.
US27 | Include individual ages | Include person's current age when listing individuals
US28 | Order siblings by age | List siblings in families by decreasing age, i.e. oldest siblings first
US29 | List deceased | List all deceased individuals in a GEDCOM file
US30 | List living married | List all living married people in a GEDCOM file
US31 | List living single | List all living people over 30 who have never been married in a GEDCOM file
US32 | List multiple births | List all multiple births in a GEDCOM file
US33 | List orphans | List all orphaned children (both parents dead and child < 18 years old) in a GEDCOM file
US34 | List large age differences | List all couples who were married when the older spouse was more than twice as old as the younger spouse
US35 | List recent births | List all people in a GEDCOM file who were born in the last 30 days
US36 | List recent deaths | List all people in a GEDCOM file who died in the last 30 days
US37 | List recent survivors | List all living spouses and descendants of people in a GEDCOM file who died in the last 30 days
US38 | List upcoming birthdays | List all living people in a GEDCOM file whose birthdays occur in the next 30 days
US39 | List upcoming anniversaries | List all living couples in a GEDCOM file whose marriage anniversaries occur in the next 30 days
US40 | Include input line numbers | List line numbers from GEDCOM source file when reporting errors
US41 | Include partial dates | Accept and use dates without days or without days and months
US42 | Reject illegitimate dates | All dates should be legitimate dates for the months specified (e.g., 2/30/2015 is not legitimate)